## Sheet1
S.No. | Task | Status | Comment
1 | Banner on home page | DONE
2 | Search result page should show promo available if a product have promo running in current date | OPEN | Showing double products
3 | Promodetail page on clicking on promo banner | OPEN | Author name is not showing
4 | Filters on promo detail page | OPEN
5 | Linking on promo deail page | OPEN
6 | Add to cart functionality on product detail page with 3 product | OPEN | Price and total count is not working properly
7 | Remove buy from sage from product detail page | OPEN | Not removing data from session
8 | In electronic version Add to cart sould not show | DONE
9 | Forthocoming product add to cart functionality | DONE
10 | Mini Cart view with price, qty and total | OPEN
11 | Cart view with product detail, price and total | OPEN | Promo detail is not showing in guest user
12 | Promo code functionality on cart view | DONE
13 | Check out as guest | DONE
14 | Review page handling with shipping address | OPEN
15 | Add, edit shipping address | OPEN
16 | Remove and change product qty in cart view and review page | OPEN
17 | Promo code on review page if applied on cart view | OPEN
18 | Check out as login user | DONE
19 | Address management for logged in user | DONE
20 | Buy one get one functionality | OPEN
21 | Mailer campaign case | OPEN
22 | Reports | OPEN
23 | Create promo code from admin | DONE
24 | Edit promo code from admin | DONE
25 | Payment via CCAvenue | DONE
26 | Thank you and failure page with order id | DONE
27 | Mails for success and failure fpr order | OPEN